## Agile Project Backlog
Agile Product Backlog
SUMMARY
Project Description
Password Manager is a Python command line application, it can keep track of all the passwords which has been set for the respective account.
PROJECT BACKLOG
ID | As a | I want to | So that | Priority | Story point | Sprint Assignment | Status
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours | Hours | Hours | Hours | Hours | Hours
1 | User | register myself | I can login and use the application | Must | 4 |  | Done
2 | User | have an option to see all my account passwords | I can secure my new password | Must | 8 |  | Done
3 | User | have an option to see my current password | I can see my current password | Must | 2 |  | Done
4 | User | have an option to see set new password | I can change my account password | Must | 2 |  | Done
5 | User | have an option to see the security level of my current password | I can secure my new password | Must | 2 |  | Done
6 | User | have an option to quit the program | I can logout | Must | 2 |  | Done

## Agile Sprint Backlog
Agile Sprint Backlog
SUMMARY
CHANGE IN SCOPE
Original Story Points |  | 14
New Points |  | 0
Total Points |  | 14
CHANGE IN SCOPE |  | 0%
SPRINT BACKLOG
ID | Backlog task | Assigned to | Story points | New points? | Release | Status | Business value | Change management notes | Initial estimate
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours
1 | As a User, I register myself, so that I can login and use the application.
1.1 | Code the… | Riyaz J |  | FALSE | 1 | Done | High
1.2 | Design the UI | Riyaz J |  | FALSE | 1 | Done | Low
2 | As a User, I want to have an option to see all my passwords, so that I can secure my current password.
2.1 | Code the… | Riyaz J |  | FALSE | 1 | Done | High
2.2 | Design the UI | Riyaz J |  | FALSE | 1 | Done | High
3 | As a User, I want to have an option to see my current passwords, so that I can see my current password.
3.1 | Code the… | Riyaz J |  | FALSE | 1 | Done | High
3.2 | Design the UI | Riyaz J |  | FALSE | 1 | Done | High
4 | As a User, I want to have an option to set new passwords, so that I can change my password.
4.1 | Code the… | Riyaz J |  | FALSE | 1 | Done | High
4.2 | Design the UI | Riyaz J |  | FALSE | 1 | Done | High
5 | As a User, I want to have an option to see the security level of my current passwords, so that I can secure my password.
5.1 | Code the… | Riyaz J |  | FALSE | 1 | Done | High
5.2 | Design the UI | Riyaz J |  | FALSE | 1 | Done | High
6 | As a User, I want to have an option to quit the program, so that I can logout.
6.1 | Code the… | Riyaz J |  | FALSE | 1 | Done | High
6.2 | Design the UI | Riyaz J |  | FALSE | 1 | Done | High